
NEWPORT PAGNELL TOWN COUNCIL
NEIGHBOURHOOD PLAN IMPLEMENTATION GROUP MEETING 
Minutes of the meeting held on Thursday 23rd March 2023

Present: Cllrs Ian Carman (Chair), Anne Butler, Philip Gage, Euan Henderson, Diane Kitchen, Richard Pearson, Phil Winsor, Alan Mills, Shar Roselman, Abi Bassett, Leani Haim (O’Neill Homer), matt Jennings (O’Neill Homer)

ITEM 1 MAR 2023/NPIG:	APOLOGIES FOR ABSENCE 
Apologies received and accepted from Cllr Hornblow

ITEM 2 MAR 2023/NPIG:	MINUTES OF THE LAST MEETING
The minutes of the virtual NPIG meeting held on Thursday 2nd February 2023 were agreed and approved as a true and correct record.

ITEM 3 MAR 2023/NPIG:	NEIGHBOURHOOD PLAN – VERSION 3 

[bookmark: _Hlk89353687]	3.1 DEVELOPMENT AND POLICY FOR NEIGHBOURHOOD PLAN

3.1.1 Strategic Environment Assessment (SEA) The meeting received the following update on the SEA process so far. The Deputy Clerk and O’Neill Homer met with AECOM on 15th March for an inception meeting. Once the scoping has taken place and the draft reports are produced, they will be sent back to NPTC for review (approx. 2 weeks) then will be sent out for statutory consultation for a further 5 weeks.  The meeting agreed to schedule Reg 14 consultations by no earlier than the end of May to allow for the SEA consultation process and review.

3.1.2 Programme of actions Leani Haim advised the meeting that, briefly, the process is Informal Consultation > MKCC Consultation > Review of Consultations > Reg 14 Consultation (6 weeks) > Submission of Modification Statement and SEA to LPA (MKCC) > Reg 16 Consultation (6 weeks) > Submission to Examiner.

NPTC has already held informal consultation sessions to give residents an early say in the Plan. Milton Keynes City Councill have also been consulted, and the Clerk and ONH are awaiting a response from David Blandamer. If MKCC are satisfied with the Plan, Reg 14 is the next step and is the statutory consultation. The report that is published at Reg 14 should be the final draft although minor amendments may still be made at this stage.

3.1.3 Public Consultations The meeting received feedback from the Consultation sessions to date and found them, overall, to be favourable towards the Plan. Concerns that were raised pertained to the lack of secondary school provision at the Tickford Field Farm development and MK East. The working Group agreed that the comments received so far did not require amendments to be made to the proposed plan. The Working Group also received a detailed response from Duncan Mason and considered his suggestions.  

3.1.3 Landowner Meetings The meeting noted that a further landowner still needs to be contacted. The Deputy Clerk advised that the previous agent for this landowner has moved on and it’s been difficult to find out who has replaced them. The Deputy Clerk will continue to attempt to make contact and arrange a meeting. 


3.1.4. O’Neill Homer Advice Note The Working Group received an advice note from O’Neill Homer on the National Planning Policy Framework (NPPF) and the Levelling Up & Regeneration Bill (LURB) consultations. NPPF changes come into force in Spring 2023. The proposals for neighbourhood planning are generally very positive, especially considering the lack of attention it received in the Planning White Paper in summer 2020.


ITEM 4 MAR 2023/NPIG:	DATE OF NEXT MEETING AND ITEMS FOR THE NEXT
AGENDA Next meeting scheduled for Thursday 11th May 2023 at 11am





Minutes subject to approval at the next meeting.

Signed______________________________	               Date__________________________________
