NEWPORT PAGNELL TOWN COUNCIL

NEIGHBOURHOOD PLAN IMPLEMENTATION GROUP
Minutes of the meeting held on Thursday 16th November 2023 at 11.00 am

Present: Cllrs Anne Butler, Ian Carman, Euan Henderson (Chair), Roger Hornblow, Diane Kitchen, Richard Pearson, and Phil Winsor. Also, Alan Mills (non-Councillor member), Leani Haim (Consultant, O’Neill Homer), Shar Roselman (Town Clerk) and Abi Bassett (Deputy Clerk).

ITEM 1 NOV 2023/NPIG:	APOLOGIES FOR ABSENCE

There were no apologies for absence.

ITEM 2 NOV 2023/NPIG:	MINUTES OF THE LAST MEETING

The meeting received and accept the minutes of the virtual NPIG meeting held on Thursday 6th July 2023.

ITEM 3 NOV 2023/NPIG:	NEIGHBOURHOOD PLAN – VERSION 3

3.1 Review of Responses The meeting received and reviewed the consultation feedback. Alongside each comment, the consultant had provided a recommendation in response and the working group agreed whether or not to accept the recommendation. See accompanying Consultation Response Worksheet for complete list of recommendations and amendments made.

3.2 Meeting with Milton Keynes Council The Working Group agreed that it was necessary to seek a meeting with the Education Department and Neighbourhood Planning Team at MKCC to discuss the library site and school provision.

3.3 Update on Landowner Meetings. The meeting received a verbal update from the Clerk on meetings with landowners. The Clerk advised that she had had telephone conversations with the remaining landowners and although they were non-committal in terms of formally responding to the consultation, they were content with the idea of identifying the land for BNG and raised no objections.

3.4 Referendum Timeline It was discussed, and agreed, that it would be preferable to tie the referendum in with upcoming elections to save the cost of paying for a separate vote. Although it was hoped that this could coincide with local elections in May 2024, due to time requirements for Reg 16 consultation and the examination period, it was agreed that it would be more realistic to try to tie the referendum in with general elections in October 2024.

ITEM 4 NOV 2023/NPIG:	DATE OF NEXT MEETING AND ITEMS FOR THE NEXT

AGENDA Next meeting 22nd February 2024.

There being no other business to discuss, the meeting closed at 12:45pm.